## Instructions (hidden)
ING: Mobilisation Action Plan
0%
Actions
| Name | Position | Initials |  | To Do | Complete |  |  | Key
| Louis Walter | Operations Manager | SD |  | 1 | 0 |  |  | To do | 1
| Megan Wordley | Operations Support Manager | SM |  | 0 | 0 |  |  | Complete | 2
| Carlos Mistry | Managing Director | CM |  | 0 | 0
| Hayley Murfin | Operations Director | HM |  | 0 | 0
| Maxwell Mckenzie | Director of Food & Operations | CD |  | 0 | 0
| Rhiannon Hestletine | Training & Development Manager | KN |  | 0 | 0
| Alice Yu | Merchandising & Brand Manager | AY |  | 0 | 0
| Tom Freer | Food | MM |  | 0 | 0
| Charlotte Hurrell | Head of Finance | CH |  | 0 | 0
| Martina Giammaria | Nutritionist | ES |  | 0 | 0
| Teri Gumpert | Head of HR | TG |  | 0 | 0
| Raffaele Colturi | Health & Safety manager | VK |  | 0 | 0
[5 empty] | 1 | 0
TIMELINE
|  |  |  | April | April | April | May | May | May | May | JUNE | Status | Statius
No | Area | Action | Actioner | 12 | 19 | 26 | 3 | 10 | 17 | 24 | 1st |  |  | Notes
| Operations | How to complete this mobilisation plan | SD | [8 empty] | FALSE | 0 | Make sure you read the directions below (D40-47)
[12 empty] | FALSE | 0
[5 empty] | 2 | [5 empty] | 2 | 0 | 2
[6 empty] | 1 |  |  |  | 1 |  | FALSE | 0
[7 empty] | 2 |  | 2 |  |  | 0 | 2
[8 empty] | 1 |  |  |  | FALSE | 0
[12 empty] | FALSE | 0
[12 empty] | FALSE | 0
Directions to complete this mobilisation plan
1 | Column D. Area- Enter the 'Area' to which each Action relates. For example, Operations, Marketing, H&S etc.
2 | Column F. Action-Write some detail, to summarise what each Action involves.
3 | Column H. Actionee- Outline the team member that will be responsible for this Action, by inputting their initials in the relevant cell.
4 | Column J-X Timeline- Decide the point in 'Time' that this Action will need to be completed, in order to ensure the Actions that follow can continue in succession undisturbed
a | Enter the number '1' for Actions that are due to be completed (this will automatically highlight the cell Green)
b | Enter the number '2' for Actions that are completed (this will automatically highlight the cell Blue)
5 | Colum AB- Make some notes, to provide yourself with reminders, or further detail on the actions you have written.

## Meeting notes (hidden)
Till purchase | Hi Raff,
Update tariff based on Paul`s email
Deep clean? | Hope you are well.
Jazz up equipment
Supplier solution and see suppliers in area | Just following on from Friday’s visit, Carlos has asked me to ask you for a couple of things:
Team advert for HC
Carlos would like to offer to Simon that we will make up for Paul’s missing salary for the past few months, then obviously just re-bill IHG.
From Hayley | Also, we will need to provide a cost comparison for cutlery. I.e, what we showed vs the next level up.
Hi There
Anything you need, just let me know.
Apologies I left IHG with a lot of notes today…. So here they are…
Thanks very much.
Max
Annette – two lines in green for you; just reply to Raff and I
Faye – you have your own section; talk to Carlos about his vision
Raff – the rest is you and I; we can catch up once accounts are out of the way!
Teri & Max; mostly fyi’s for you! | Hi Simon
Yes no worries; how are the fixed to the wall? I am wondering how much weight they will hold?
Diary Dates For Meetings
Teri, Max, Raff, Hayley – visit Denham; Initial TUPE meeting: What do we want to take with us to Windsor (small / light equipment) | We can do a combination of retail items like coffee tings; GEC sauces etc… maybe some plants or seasonal produce…. Once we have more of a feel for the space it will be easier to decide.
Teri, Raff, Hayley – Visit Burton;- TUPE and how will we revamp the space (Max not sure if you will want to join us.. or can we take Chris?)
4th November – Raff & Max: Carlos will organise a trip for you to go with him and see Windsor (also taking Paul the current Chef Manager) between 11am and 1pm | Thanks
Wilson Vale – I am waiting for them to confirm a call this week ton discuss stock handover (IHG own all stock and want us to keep anything unopened) plus when we can do the initial TUPE meeting | H
Key Dates – already in your diaries | From: Shaw, Simon <Simon.Shaw1@ihg.com>
28th November Opening Day for Denham and Burton – keep everything as is | Sent: 08 November 2022 12:10
We will have access to Windsor for deliveries / set up / training | To: Hayley Murfin <hayley@goodeatingcompany.com>
12th December Opening Day / Revamp Burton opening Day | Subject: Add to list for next week
Free Food all week at both sites
15th December Welcome Party – Drinks and Canapes
20th December Free Christmas Lunch both sites
22nd December Welcome Party – Drinks and Canapes
23rd December Brunch until 12:00h | Need to fill these shelfs in the cafe is that something you can do also they are 300 deep
The Cafes will be open between Christmas and New Year; offer to be confirmed. Proposed Coffee and Panini
Thanks
Faye:
Branding / Create an identify for the Cafes at Windsor and Burton (menu templates etc)
Operations: | Simon
Produce a proposal to revamp Burton
Suggest Uniforms (Based on team; probably along the lines of BDC) Client to sign off
Financials:
Tariff Increase proposal. Simplify current Tariff (e.g., All mains £3.75)
We only need to cover food cost plus VAT
Team:
Paul – Chef Manager; Teri we need to discuss as ideally, we want a Head Chef and a General Manager
Depending on who TUPE over we may need to restructure
Barista – I have asked Rhiannon to start recruiting for a Barista in Windsor as current Barista (Dickson) will not travel
Light Equipment
This must be invoiced end of November – Invoice the full cost; but keep some back for phase two so we can purchase more once operational
Add to our list
Glasses, Plates and cutlery need to be approved
Trollies for hospitality (as per ARUP)
Stainless steel trollies
Kitchen bins – check if required
Autocham hot trolley – to get hot food from Kitchen to 4th Floor if required.
Hot plates required for hospitality (could we also use the lamps like we had at Sony Music?/)
Hospitality Ground Floor x 30 covers
Wine / Champagne glasses - get approx. 30. Any larger events we can hire them
Hospitality served on 4th floor (boardroom on this level) ensure enough for 200 covers
Hot fork buffets |  | Hi Raff
Cold Fork Buffets
Sandwich lunches |  | The pop up costs can be recharged on the same invoice as the free food week commencing 12th December
Ty
Café Offer: |  | H
Ensure Decaffeinated Tea
Fresh Lemon & Ginger Tea
Ensure Jacket Potatoes available daily (this can be reviewed and removed later)
All soft drinks / Minerals are on cans (no glass or plastic)
All hot drinks served in China
Food served on China (have takeaway boxes available on request)
Mondays – Free Fruit every Monday
Ensure we have some prominent Bistrot Coffee materials; back story, sustainability credentials, recycling of tins etc
Tea Point Equipment
4 tea points; 120 people per floor
Teaspoons
12oz mugs coloured (need to be approved)
Glasses (Inverness Highball possibly or as per ARUP 12oz size)
No plates, bowls, knives or forks required
Tea Point Offer
Enveloped tea bags – Annette what is the most sustainable option clipper??
Crowne Plaza coffee beans – Client to share UC account details so we can order
Gas for water machines – from BOC we will need to supply
Cordials – we will need to supply; ideally decanted into a plain bottle
Oat Milk
Semi Skimmed Milk
Skimmed Milk
Notes:
IHG will organise the music themselves no 8Trakx requirement
We need to apply for the Windsor alcohol license
Check if we need a alcohol license for Burton / Branston
Week 1 we need Sherri or Kristina to support reception at Windsor - I have sent Ana a diary invite with this on
All bins front of house will be built in; waiting confirmation of what colour bin bag is to be used for what waste.
Expect it to be segregated into
Food
Oil
Paper / cardboard
Recycling
Everything else